## Sheet1
RISKID | IDENTIFIED RISK | T OR O
LEGAL RISK
1 | التاخير فى اصدار التراخيص | T
2 | حدوث نذاعات بين اطراف التعاقد | T
3 | تصفيه اعمال مقاول الباطن | T
DESIGN
4 | وجود خطاء في التصميم | T
5 | التغيير فى التصميم المطلوب الخاص لبند معيا | T
6 | عدم التنسيق | T
ORGNAIZATIONِِِِ RISK
7 | تاخير الموارد | T
8 | عدم توافر الطرق والمواصلات للموقع | T
9 | كميات غير دقيقه | T
10 | الانتهاء من الاعمال قبل الموعد | O
11 | نقص متطلبات شروط السلامة | T
12 | عدم توافر ابراج اتصالات | T
POOR QUALITY
13 | طلب المالك من المقاول بعمل فحص للعيوب | T
14 | عدم دقه الخلطه الخرسانيه | T
15 | عمل اختبارات غير موجوده في الاشتراطات | T
CONSTRACTION
16 | الاخطاء اثناء التنفيذ | T
17 | تطبيق اساليب ابداعيه او طرق عمل جديده بالتنفيذ | O
18 | حدوث عطل في المعدات | T
19 | ان يقوم المالك بتوريد بعض الخامات بنفسه | O
20 | عدم مطابقه المقاولين اثناء التنفيذ للرسومات الهندسيه | T
SITE RISK
21 | عند وجود عوائق فى مكان التنفيذ | T
ENVIRONMEN
22 | الامطار | T
23 | حروب | T
24 | الامراض والفيروسات | T
25 | عند وجود تلوث فى منطقه العمل تودى الى تعطيل التنفيذ | T
FINANCIAL RISK
26 | ارتفاع اسعار المواد المستخدمه | T
27 | افلاس المقاول | T
28 | ارتفاع مرتبات المهندسين | T
29 | التاخر في دفع المستخلص | T
30 | التغيير فى اسعار الصرف | T
ECONOMIC
31 | التضخم | T
32 | الانحرافات الحاصله فى التقديرات الضريبيه | T
MATRIAL
33 | عدم توافر بعض المواد | T
34 | حدوث خطاء عند التشوين يسبب فى تلف المواد | T
35 | مشاكل فى التوريد | T

## Sheet2
|  | ID | T/o | Prob. | IMPACT |  | RISK SCORE |  | RISK RATE |  | SCORE
[5 empty] | TIME | COST | TIME | COST | TIME | COST
|  | 1 | T | 50% | 50% | 50% | 25% | 25% | HIGH | HIGH | 25%
|  | 2 | T | 55% | 30% | 70% | 16.5% | 38.5% | HIGH | HIGH | 38.5%
|  | 3 | T | 55% | 70% | 70% | 38.5% | 38.5% | HIGH | HIGH | 39%
|  | 4 | T | 80% | 70% | 70% | 56% | 56% | HIGH | HIGH | 56%
|  | 5 | T | 50% | 30% | 30% | 15% | 15% | MEDIUM | MEDIUM | 15%
|  | 6 | T | 55% | 90% | 90% | 49.5% | 49.5% | HIGH | HIGH | 50%
|  | 7 | T | 30% | 80% | 50% | 24% | 15% | HIGH | MEDIUM | 15%
|  | 8 | T | 50% | 40% | 30% | 20% | 15% | HIGH | MEDIUM | 15%
|  | 9 | T | 30% | 30% | 30% | 9% | 9% | MEDIUM | MEDIUM | 9%
low | 5% | 10 | T | 20% | 10% | 50% | 2% | 10% | low | MEDIUM | 10%
mediom | 15% | 11 | T | 40% | 30% | 60% | 20% | 24% | HIGH | HIGH | 24%
high | 75% | 12 | T | 55% | 60% | 50% | 33% | 27.5% | HIGH | HIGH | 28%
|  | 13 | T | 20% | 50% | 70% | 10% | 14% | MEDIUM |  | 14%
|  | 14 | T | 70% | 80% | 60% | 56% | 42% | HIGH | HIGH | 42%
|  | 15 | T | 40% | 70% | 80% | 28% | 32% | HIGH | HIGH | 32%
|  | 16 | T | 80% | 80% | 50% | 64% | 40% | HIGH | HIGH | 40%
|  | 17 | T | 60% | 20% | 50% | 12% | 30% | MEDIUM | HIGH | 30%
|  | 18 | T | 70% | 70% | 50% | 49% | 35% | HIGH | HIGH | 35%
|  | 19 | T | 50% | 10% | 10% | 5% | 5% | low | LOW | 5%
|  | 20 | T | 60% | 70% | 70% | 42% | 42% | HIGH | HIGH | 42%
|  | 21 | T | 20% | 70% | 70% | 14% | 14% | MEDIUM |  | 14%
|  | 22 | T | 20% | 70% | 60% | 14% | 12% | MEDIUM | MEDIUM | 12%
|  | 23 | T | 5% | 80% | 80% | 4% | 4% | low | LOW | 4%
|  | 24 | T | 20% | 70% | 70% | 14% | 14% | MEDIUM | MEDIUM | 14%
|  | 25 | T | 10% | 20% | 30% | 2% | 3% | low |  | 3%
|  | 26 | T | 70% | 40% | 70% | 28% | 49% | HIGH | HIGH | 39%
|  | 27 | T | 20% | 70% | 60% | 14% | 12% | MEDIUM | MEDIUM | 12%
|  | 28 | T | 10% | 10% | 70% | 1% | 7% | low | MEDIUM | 7%
|  | 29 | T | 40% | 50% | 10% | 20% | 4% | HIGH | LOW | 4%
|  | 30 | T | 30% | 20% | 50% | 6% | 15% | MEDIUM |  | 15%
|  | 31 | T | 40% | 20% | 60% | 8% | 24% | MEDIUM | HIGH | 24%
|  | 32 | T | 30% | 30% | 50% | 9% | 15% | MEDIUM |  | 15%
|  | 33 | T | 30% | 60% | 30% | 18% | 9% | HIGH | MEDIUM | 9%
|  | 34 | T | 30% | 50% | 70% | 15% | 21% | MEDIUM | HIGH | 21%
|  | 35 | T | 30% | 40% | 50% | 12% | 15% | MEDIUM |  | 15%

## Sheet4
ID | T/o | Prob. | IMPACT |  | RISK SCORE |  | RISK RATE |  | SCORE
|  |  | TIME | COST | TIME | COST | TIME | COST |  | Description | [6 empty] | response | mitigation strategy
4 | T | 80% | 70% | 70% | 56% | 56% | HIGH | HIGH | 56% | Design error | Design error | Design error | Design error | Design error | Design error | Design error | ACCEPT
6 | T | 55% | 90% | 90% | 49.5% | 49.5% | HIGH | HIGH | 50% | Lack of coordination | Lack of coordination | Lack of coordination | Lack of coordination | Lack of coordination | Lack of coordination | Lack of coordination | Use of BIM technology
14 | T | 70% | 80% | 60% | 56% | 42% | HIGH | HIGH | 42% | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Inaccuracy in concrete mix | Conducting necessary tests before handover
20 | T | 60% | 70% | 70% | 42% | 42% | HIGH | HIGH | 42% | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | Non-conformance of contractors to engineering drawings | ACCEPT
16 | T | 80% | 80% | 50% | 64% | 40% | HIGH | HIGH | 40% | Errors during execution | Errors during execution | Errors during execution | Errors during execution | Errors during execution | Errors during execution | Errors during execution | ACCEPT
3 | T | 55% | 70% | 70% | 38.5% | 38.5% | HIGH | HIGH | 39% | Contractor's work clearing | Contractor's work clearing | Contractor's work clearing | Contractor's work clearing | Contractor's work clearing | Contractor's work clearing | Contractor's work clearing | Contract warranties are adhered to
26 | T | 70% | 40% | 70% | 28% | 49% | HIGH | HIGH | 39% | Increase in prices of used materials | Increase in prices of used materials | Increase in prices of used materials | Increase in prices of used materials | Increase in prices of used materials | Increase in prices of used materials | Increase in prices of used materials | Increase in unit price measurement
2 | T | 55% | 30% | 70% | 16.5% | 38.5% | HIGH | HIGH | 38.5% | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | Occurrence of disputes between contracting parties | ACCPET
18 | T | 70% | 70% | 50% | 49% | 35% | HIGH | HIGH | 35% | Equipment breakdown | Equipment breakdown | Equipment breakdown | Equipment breakdown | Equipment breakdown | Equipment breakdown | Equipment breakdown | With the existence of a court to resolve disputes
15 | T | 40% | 70% | 80% | 28% | 32% | HIGH | HIGH | 32% | Performing tests not included in specifications | Performing tests not included in specifications | Performing tests not included in specifications | Performing tests not included in specifications | Performing tests not included in specifications | Performing tests not included in specifications | Performing tests not included in specifications | Agreement on the price of tests not included in the specifications
17 | T | 60% | 20% | 50% | 12% | 30% | MEDIUM | HIGH | 30% | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Applying creative methods or new work methods in execution | Accpet
12 | T | 55% | 60% | 50% | 33% | 27.5% | HIGH | HIGH | 28% | Unavailability of some materials | Unavailability of some materials | Unavailability of some materials | Unavailability of some materials | Unavailability of some materials | Unavailability of some materials | Unavailability of some materials | TRANSFARE
1 | T | 50% | 2% | 50% | 45% | 25% | HIGH | HIGH | 25% | Delay in issuing permits | Delay in issuing permits | Delay in issuing permits | Delay in issuing permits | Delay in issuing permits | Delay in issuing permits | Delay in issuing permits | TRANSFARE
11 | T | 40% | 30% | 60% | 20% | 24% | HIGH | HIGH | 24% | Lack of safety requirements | Lack of safety requirements | Lack of safety requirements | Lack of safety requirements | Lack of safety requirements | Lack of safety requirements | Lack of safety requirements | Adherence to safety conditions
31 | T | 40% | 20% | 60% | 8% | 24% | MEDIUM | HIGH | 24% | Inflation | Inflation | Inflation | Inflation | Inflation | Inflation | Inflation | Accpet
l

## Sheet3
| Threat |  |  |  |  | Opportuaities
| Risk Score = Probability * Impact |  |  |  |  | High(RED) / Med(YEL) / Low(GRN)
| Impact |  |  |  |  | Impact
Probability | 0.05 | 0.1 | 0.2 | 0.4 | 0.8 | Very High | High | Med | Low | Very Low
0.1 | 0.005 | 0.01 | 0.02 | 0.04 | 0.08 | Med | Low | Low | Low | Low
0.3 | 0.015 | 0.03 | 0.06 | 0.12 | 0.24 | High | Med | Med | Low | Low
0.5 | 0.025 | 0.05 | 0.1 | 0.2 | 0.4 | High | High | Med | Low | Low
0.7 | 0.035 | 0.07 | 0.14 | 0.28 | 0.56 | High | High | Med | Med | Low
0.9 | 0.045 | 0.09 | 0.18 | 0.36 | 0.72 | High | High | High | Med | Low